## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Assessment Questions
| Table 1 | Assessment Questions
KT Evidence Register
| Table 1 | KT Evidence Register
Workflow and Telemetry Map
| Table 1 | Workflow and Telemetry Map
Gap Analysis
| Table 1 | Gap Analysis
Pilot Plan
| Table 1 | Pilot Plan

## Assessment Questions
Assessment Questions
Twelve focused questions, pre-filled from KT evidence where supported. Update status and evidence during owner review.
ID | Area | Recommended question | Why it matters | What KT already tells us | What still needs confirmation | Suggested owner | Evidence to collect | Priority | Recommendation | Status | Owner | Due date | Answer / notes | Evidence link
R1 | Workflow selection | Which specific governance E2E workflow should represent the first assessment, and what does it prove? | Choose a bounded workflow so evidence can be traced end to end. | Several candidate workflows were discussed: location enforcement, central logging, technology management, MMS and Terraform state. No pilot workflow was approved in the KTs. | Confirm workflow owner, purpose, expected result and why it is representative. Do not commit to a pilot yet. | QA lead / workflow owner | Workflow name; pipeline URL; test purpose/assertions; representative run | High | Select one candidate; verify scope before pilot | Needs owner confirmation
R2 | Execution path | For that workflow, which pipeline job and PowerShell/Pester code run on which agent pool and runtime? | The runtime and agent determine feasible instrumentation and what logs are available. | Custom agents are described as AKS-hosted pods with Dev, Non-Prod, Prod-Dev and Prod-Prod pools; hosted and SR Ubuntu pools also exist. Exact workflow-to-pool mapping is not established. PR checks include PowerShell analysis/unit tests; trigger patterns vary. | Confirm pipeline/job, trigger, pool, image, PowerShell version, Pester version and whether code runs in pipeline agent or another runtime. | QA / pipeline owner; DevSecOps for agent details | Pipeline/job URL; agent pool/image; runtime versions; relevant code path | High | Map actual workflow; do not infer from pool names | Needs owner confirmation
R3 | Target and permissions | What is the actual Azure target for a run, and what identity/permissions let it operate there? | Target scope and execution environment are separate; elevated permissions may prevent local reproduction. | Some governance tests use test subscriptions in the production tenant; Dev-tenant testing and production-specific PIM testing also exist. Some tests cannot run locally due to elevated permissions. | Confirm tenant, subscription/resource scope, service connection/identity, role assignments and approved test boundaries. | QA/pipeline owner; subscription/policy owner | Pipeline variables/config (no secrets); service connection identity name; scope and role evidence | High | Verify target before any test or pilot | Needs owner confirmation
R4 | Current visibility | Where are the selected workflow’s run logs, test results, failures and duration available today, and are they centrally searchable? | Establish the current baseline before adding telemetry. | Pipeline logs/results are available in Azure DevOps. Location-enforcement E2E logs/results were explicitly described as not centrally ingested in that example. | Confirm current run evidence and whether it is searchable centrally for the selected workflow; record retention only if verified. | QA / pipeline owner; OaaS for central search confirmation | Run URL; test results; failure output; duration; central query or confirmation of absence | High | Collect one representative run and search evidence | Needs owner confirmation
R5 | Signal inventory | Which existing signal paths apply to this workflow—Azure Policy data, Function logs/custom tables/DCRs, Activity Logs/queues, LaaS diagnostics and Sensor alerts—and where is each stored? | Avoid duplicating native signals and identify the actual path for this component. | LaaS is a company-wide sink for configured Azure resource diagnostic data; some data routes through Event Hub. Some Function logs use DCRs/custom Log Analytics tables. MMS policy-sensor flow queries non-compliant results and sends Sensor alerts. Exact paths vary by component. | Inventory only the selected workflow; confirm actual tables, queries, destinations, relevant Function/queue dependencies and whether each signal is enabled. | Policy/component owner; logging owner; Sensor owner | Architecture/path sketch; table/query names; sample records; destination evidence | High | Build evidence-based signal map; mark unknown links explicitly | Needs owner confirmation
R6 | Telemetry delivery | For the chosen policy test, does the test prove only that configuration/outcome is present, or also that resulting telemetry arrives at its destination? | Configuration of diagnostic settings does not prove successful end-to-end delivery. | Central-logging E2E tests validate diagnostic settings; the KT example did not validate actual log arrival from the specific test resource in LaaS. | Confirm whether the selected workflow has a separate arrival/query assertion and produce a sample record if it does. | QA / logging owner | Test assertions; diagnostic setting; destination query; timestamped sample record | High | Separate configuration checks from delivery checks | Pre-filled from KT
R7 | Governance outcome | What is the source of truth for the governance outcome, and how long after deployment/run does it become available? | A green pipeline can coexist with delayed or non-compliant governance state. | Azure Policy evaluation can be asynchronous; tests poll/wait and fail if expected state is not achieved. Exact source of truth and timing vary by workflow and are not fully established. | Confirm authoritative query/API/table, expected state, polling window and measured delay for the chosen workflow. | Policy framework/component owner; QA | Policy assignment/compliance result; test assertion; timestamps for run and outcome | High | Measure run-to-outcome delay for selected workflow | Needs owner confirmation
R8 | Correlation | Can one pipeline run be linked to the resulting policy outcome, remediation and Sensor alert? What join keys exist today? | Correlation enables investigation across execution, control outcome and alerting. | Policy-sensor components query non-compliant MMS policy results and send Sensor alerts; later runs can update alerts after compliance returns. Consistent correlation across pipeline run, outcome, remediation and alert is not established in the KTs. | Confirm existing IDs/timestamps/tags and demonstrate one joined example; do not assume a common correlation ID exists. | Policy/Sensor owner; QA/pipeline owner | Pipeline run ID; policy/assignment/resource identifiers; remediation record; Sensor alert reference | High | Test traceability with one real run and alert/outcome | Needs owner confirmation
R9 | Failure detection | Which failures in this workflow are detected and alerted on, where do alerts go, and how are permission, Azure delay, script failure and missing telemetry distinguished? | Clarify actionable detection rather than simply collecting more logs. | Some Functions have runtime-error and no-logs-in-24-hours alerts; Sensor alerts cover non-compliant MMS policy results. This coverage is not established for all components/workflows. | Confirm applicable rules, destinations, thresholds and ability to distinguish failure classes for the chosen workflow. | Component owner; QA; Sensor/alert owner | Alert rules and destinations; sample alert; known failure behavior; runbook if available | High | Inventory only applicable alerts and test evidence | Needs owner confirmation
R10 | OaaS integration | What is the approved OaaS instrumentation/export path for this exact PowerShell runtime and agent environment? | A discussed SDK is not proof that a supported, approved end-to-end path exists. | PowerShell OTel SDK and Function OTel instrumentation were discussed, but no approved exporter, endpoint, protocol, authentication, network path or completed pipeline integration was established. | Ask OaaS and DevSecOps to confirm supported runtime, exporter/collector pattern, protocol, authentication, TLS, egress and short-lived-job flush behavior. | OaaS team; DevSecOps/network owner | Written approved pattern; prerequisites; example for actual runtime/agent; connectivity evidence | High | Resolve before adding instrumentation or changing code | Needs OaaS decision
R11 | Signal destination | Which signals should go to OaaS/Elastic, and which should remain in Azure-native logging or LaaS? | Define a clear destination and avoid duplicating data or bypassing approved logging paths. | Existing paths include Azure DevOps logs/results, Azure Policy data, LaaS diagnostics, Log Analytics custom tables/DCRs and Sensor alerts. No final decision on which signals additionally go to Elastic was established. | Agree signal-by-signal destination, ownership, retention/access controls and whether existing native sources can be queried or linked instead of re-exported. | OaaS team; platform logging owner; component owner | Signal-to-destination matrix; approved architecture/decision | High | Make a small scoped decision for selected workflow | Needs OaaS decision
R12 | Pilot decision | After target and export approvals are confirmed, what is the smallest safe pilot, and what evidence constitutes success or safe failure? | Prove value with one approved workflow before expanding. | A policy E2E workflow was proposed as a candidate, not approved. Target scope must be verified; a controlled failure test was not established as approved in KT. | Agree normal-run success criteria, searchable evidence, timestamps/correlation, controlled failure safety, cleanup/rollback and go/no-go owner. | Prem / QA / target owner / OaaS team | Approved plan; baseline run; destination query; optional approved failure run; go/no-go record | Medium | Pilot only after scope, permissions and export path approval | Needs owner confirmation

## KT Evidence Register
KT Evidence Register
Session references and evidence are drawn from the available KT assessment summary. Exact transcript timestamps were not available; they are intentionally not fabricated.
Evidence ID | Session title | Finding | Status (confirmed/proposed/unresolved/not established) | Related question IDs | Follow-up/evidence needed
E01 | Azure DevOps Quality Pipelines, Test Coverage, and Agent-Image Scanning KT | Custom Azure DevOps agents described as AKS-hosted pods; separate Dev, Non-Prod, Prod-Dev and Prod-Prod pools. Hosted agents and SR Ubuntu pools also used. Exact pipeline-to-pool mapping not established. | Confirmed | R2 | Map the selected pipeline to its actual pool, image and runtime.
E02 | Azure DevOps Quality Pipelines, Test Coverage, and Agent-Image Scanning KT | Basic PR quality pipelines run on pushes/PR updates and include linting, PowerShell Script Analyzer and unit tests; new/changed code has a 50% coverage requirement with legacy exceptions. | Confirmed | R2 | Confirm whether and how these checks apply to the selected workflow.
E03 | Azure DevOps Quality Pipelines, Test Coverage, and Agent-Image Scanning KT | Some compliance-analyzer checks were advisory rather than merge blockers at the time of the KT. | Confirmed (time-bound) | R2, R9 | Confirm current enforcement only if relevant to selected workflow.
E04 | Azure DevOps Quality Pipelines, Test Coverage, and Agent-Image Scanning KT | The pipeline execution agent/environment differs from the Azure target scope; some tests require elevated permissions and cannot be run locally. | Confirmed | R2, R3 | Capture actual pool/runtime separately from tenant/subscription/resource target.
E05 | Azure DevOps Quality Pipelines, Test Coverage, and Agent-Image Scanning KT | Some governance test subscriptions are in the production tenant; Dev-tenant testing and production-specific PIM testing also exist. | Confirmed | R3 | Verify exact tenant and subscription for the selected run.
E06 | Azure DevOps Quality Pipelines, Test Coverage, and Agent-Image Scanning KT | Trigger patterns vary by workflow: PR/push, merge, manual and scheduled/nightly examples. | Confirmed | R2 | Record the selected workflow's actual trigger.
E07 | Azure Location Enforcement Guardrail: Landing Zones, Tests, and Region-Data Source | Location-enforcement E2E pipeline logs/results were retained in Azure DevOps and explicitly not centrally ingested in the KT example. | Confirmed (specific example) | R4, R11 | Confirm whether this remains true and whether selected workflow differs.
E08 | Azure Location Enforcement Guardrail: Landing Zones, Tests, and Region-Data Source | Azure Policy evaluation can be asynchronous; tests poll/wait and fail if the expected state is not achieved. | Confirmed | R7, R9 | Capture timestamps and authoritative outcome evidence for selected workflow.
E09 | Azure Central Logging Policies, Diagnostic Testing, and Framework Ownership KT | Central-logging E2E tests validate diagnostic settings, not actual log arrival at LaaS for the specific test resource. | Confirmed (specific test limitation) | R6 | Check whether an independent destination query or arrival assertion exists.
E10 | Azure Central Logging Policies, Diagnostic Testing, and Framework Ownership KT | LaaS is a company-wide sink for configured Azure resource diagnostic data; some diagnostic data is routed through Event Hub. | Confirmed | R5, R11 | Trace the selected resource's actual configured destination.
E11 | Azure MMS Policies, Sensor Alerts, Logging, and Test-Management Planning KT | Some Function application logs use DCR-based collection and custom Log Analytics tables; the Function-to-DCR wiring was not fully understood during the KT. | Unresolved | R5 | Confirm actual Function, DCR, destination and sample record.
E12 | Azure MMS Policies, Sensor Alerts, Logging, and Test-Management Planning KT | Some Function components have runtime-error and no-logs-in-24-hours alerts; coverage was not established for all Functions. | Confirmed (limited scope) | R9 | Identify which alerts apply to the selected workflow.
E13 | Azure MMS Policies, Sensor Alerts, Logging, and Test-Management Planning KT | Policy-sensor components query non-compliant MMS policy results and send alerts to the Sensor platform; later runs can update alerts after compliance returns. | Confirmed | R5, R8, R9 | Collect one example alert and identify available join keys.
E14 | Azure Central Terraform State Storage, DR Testing, and Test Documentation | Terraform-state tests covered functional and DR behavior, but the state component was explicitly said to lack operational storage-health alerts/observability. | Confirmed gap (as stated in KT) | R1, R9 | If selected as comparison/candidate, define minimal storage-health monitoring evidence.
E15 | Azure MMS Policies, Sensor Alerts, Logging, and Test-Management Planning KT | PowerShell OTel SDK and Function OTel instrumentation were discussed; no approved exporter, endpoint, protocol, authentication, network path or completed pipeline integration was established. | Proposed/planned; integration not established | R10, R11 | Obtain an approved pattern from OaaS for actual runtime/agent.
E16 | Azure MMS Policies, Sensor Alerts, Logging, and Test-Management Planning KT | Sandbox resources were described as automatically removed after about 90 days, but cleanup implementation and failure monitoring were not established. | Unresolved / not established | R9 | Verify actual cleanup workflow, schedule and failure alerts before relying on it.

## Workflow and Telemetry Map
Workflow and Telemetry Map
Compact map of candidate workflows; agent location and Azure target scope are kept separate.
Workflow | Trigger | Execution location | Target scope | Azure/service dependencies | Success evidence | Failure handling | Current result/log locations | Known uncertainty
Policy deployment and assignment | Pipeline/trigger varies by component; exact trigger not established | Azure DevOps agent/pipeline; exact runtime per workflow not established | Tenant/subscription/policy scope varies; confirm selected run | Azure Policy; service connection/identity; target resources | Pipeline status plus policy assignment/compliance outcome; exact authoritative evidence varies | Policy evaluation may be asynchronous; tests may poll/wait | Pipeline logs/results in Azure DevOps; policy result source varies | Exact pipeline, target, identity, outcome source and timing not established
Central logging policy E2E test | E2E pipeline; exact trigger not established | Azure DevOps agent; exact pool/runtime not established | KT describes designated test subscription in production tenant for central-logging testing | Diagnostic settings; Azure resource diagnostics; LaaS; some paths through Event Hub | Test checks diagnostic-setting configuration | Specific-resource log arrival is not asserted by the described test | Pipeline logs/results in Azure DevOps; LaaS destination is configured but arrival not proven by that test | Actual destination query/sample log arrival for test resource not established
Technology Management guardrail test | Trigger pattern varies; exact selected trigger not established | Azure DevOps agent; exact pool/runtime not established | Target scope for a specific run not established | Azure Policy; allow/deny expectations; exemptions may be relevant | Tests assert expected deny/allow outcomes | Azure Policy timing and test waits may affect outcome; exact failure handling not fully established | Pipeline logs/results in Azure DevOps; policy outcome source to verify | Exact run target, outcome query and end-to-end telemetry path
VM Governance E2E test | Not established in KT summary | Execution agent/runtime not established | VM/subscription/tenant target not established | Azure VM and relevant governance controls; exact dependencies not established | Expected test assertions; specific evidence not established | Not established in KT | Not established in KT | Workflow detail, run evidence, signals and alerts need owner confirmation
MMS policy-sensor alert flow | Policy evaluation and subsequent component processing; exact trigger/schedule not established | Sensor/policy-sensor component runtime not established | MMS policy scope; exact tenant/subscription/resource for a sample not established | Azure Policy non-compliance results; policy-sensor component; Sensor platform | Non-compliant MMS policy result can generate Sensor alert; later compliant runs can update alert | Policy evaluation can be asynchronous; exact end-to-end timing not established | Sensor alert records; source query/table needs confirmation | Join keys linking pipeline, policy result, remediation and alert not established
Function-based governance automation | Event/queue/schedule/pipeline triggers vary; selected Function trigger not established | Azure Function runtime, distinct from general pipeline agent execution | Target scope depends on function; not established for a specific workflow | Azure/Entra/Storage/Monitor APIs; queues/events/schedules may apply; some DCR/custom-table logging | Runtime logs/custom tables for some components; specific success evidence varies | Some Function components have runtime-error and no-logs-in-24-hours alerts; not universal | Some logs go to DCR-based custom Log Analytics tables; exact Function-to-DCR wiring unresolved | Function identity, trigger, target scope, DCR wiring and alerts need confirmation
Terraform state backup/DR | Test/manual workflow; exact trigger not established | Pipeline/agent mapping not established | Centralized state storage, with state organized by subscription ID per KT context | Azure Storage state service; backup/restore/DR behavior | Functional and DR tests were described | Operational storage-health alerts/observability explicitly lacking per KT | Test documentation/reporting location not fully established; Confluence report was proposed, not confirmed | Current health monitoring, alert owner and run evidence need confirmation

## Gap Analysis
Gap Analysis
Evidence-led findings. Absence of evidence is not presented as proof of a defect.
Gap ID | Topic | Finding | Classification (confirmed gap / potential gap / not enough evidence) | Operational impact | Remaining uncertainty | Recommended next step | Related question IDs | Owner
G1 | Pipeline visibility | Location-enforcement E2E logs/results were retained in Azure DevOps and not centrally ingested in the KT example. | confirmed gap | Cross-run search and trend analysis may require manual access to Azure DevOps. | Whether this is still current and whether other workflows differ. | Confirm current state; use as a scoped baseline, not a platform-wide claim. | R4, R11 | QA / pipeline owner; OaaS
G2 | Logging delivery validation | Central logging E2E test checks diagnostic settings but not actual arrival of logs from the specific test resource at LaaS. | confirmed gap | Configuration can pass while end-to-end log delivery remains unproven. | Whether another test/query separately validates arrival. | Add/identify an approved destination-side verification for selected resource. | R6 | QA / logging owner
G3 | Terraform state health | Terraform state component was described as lacking operational storage-health alerts/observability. | confirmed gap | Storage/service degradation may not be surfaced by functional/DR tests alone. | Current monitoring may have changed after KT; verify before action. | Confirm current monitoring and define minimal health signal/alert if still absent. | R1, R9 | Terraform state component owner
G4 | Function logging path | Function-to-DCR wiring was not fully understood during KT for some custom-table logging. | potential gap | Missing or misrouted logs could be difficult to diagnose. | Exact Function, DCR, destination and sample record unknown. | Trace one Function event through collection to the actual table. | R5 | Function/component owner; logging owner
G5 | Cross-system correlation | No transcript evidence establishes consistent correlation across pipeline run, policy outcome, remediation and Sensor alert. | not enough evidence | Investigation may require manual joins if identifiers/timestamps are not aligned. | This is absence of evidence in reviewed KTs, not proof correlation is impossible or absent. | Demonstrate one workflow trace and document available join keys. | R8 | QA / policy framework / Sensor owner
G6 | OTel export approval | PowerShell OTel SDK and Function instrumentation were discussed; approved exporter/endpoint/protocol/auth/network path and completed integration were not established. | potential gap | Unapproved or unsupported export could fail or conflict with platform controls. | OaaS may have a standard not captured in KTs. | Request approved path for the exact runtime/agent; do not implement before confirmation. | R10, R11 | OaaS team; DevSecOps/network owner
G7 | Pilot execution map | Exact pipeline-to-agent mapping and target scope for a selected pilot are not established. | not enough evidence | Wrong assumptions about environment or permissions could make pilot invalid or unsafe. | Need one actual run configuration and approved target. | Capture pipeline/job/pool/runtime separately from tenant/subscription/scope and identity. | R2, R3, R12 | QA/pipeline owner; subscription/policy owner
G8 | Schema/retention | Schema inconsistency or retention defects were not established as general defects in the KTs. | not enough evidence | Potential downstream query issues should not be reported as verified defects without evidence. | Actual schema and retention for selected tables not fully inventoried. | Inspect selected table/query and retention only if relevant; do not classify as confirmed defect. | R5, R9, R11 | Logging/component owner

## Pilot Plan
Pilot Plan
Pilot is conditional on target-scope and OaaS approval. A policy E2E workflow is a candidate, not a decision.
Phase | Activity | Owner role | Entry criteria | Evidence/output | Safety check | Status
1. Select workflow | Choose one representative governance E2E workflow; define what it proves. | QA lead / workflow owner | Candidate selected; owner agrees on scope | Workflow name, test purpose, pipeline/job URL | Verify tenant/subscription/resource target and service connection; no run until approved | Not started
2. Confirm target and identity | Validate actual Azure target, service connection/identity and required permissions. | QA/pipeline owner; subscription/policy owner | Workflow candidate identified | Target tenant/subscription/scope; identity name; role/permission evidence (no secrets) | Keep execution agent and Azure target as separate fields; do not assume Non-Prod | Not started
3. Map current signals | Collect current pipeline result, policy outcome, relevant Function/Log Analytics/DCR, LaaS and Sensor evidence that actually applies. | QA; policy/component owner; logging/Sensor owners | Target and workflow confirmed | Representative run; outcome query/result; relevant log/alert sample or documented absence | Use read-only evidence first; do not alter production controls | Not started
4. Confirm OaaS export | Ask OaaS/DevSecOps for approved integration for the actual PowerShell runtime and agent environment. | OaaS team; DevSecOps/network owner | Runtime, agent pool and target known | Approved export pattern and prerequisites; endpoint/protocol/auth/TLS/network and short-job flush behavior | No code changes or telemetry export before approval | Not started
5. Run normal test | Run one normal test in the approved target and verify data is searchable in the approved destination. | QA/pipeline owner; OaaS | Target and export approach approved | Run ID/time; expected outcome; destination query/sample; end-to-end timing | Approved target only; retain existing native evidence | Not started
6. Controlled failure (conditional) | If explicitly approved, run one controlled failure/non-compliance case and verify detection, alert and cleanup/rollback. | QA; target owner; component/Sensor owner; OaaS | Normal run works; explicit failure-test approval | Failure signal; alert/result; correlation; cleanup/rollback evidence | Do not induce non-compliance or modify controls without written scope and rollback plan | Not started
7. Go/no-go | Review evidence and decide whether to stop, adjust or expand to another workflow. | Prem / QA / target owner / OaaS | Normal run completed; failure test only if approved | Short results summary; known limitations; decision and next action | No broad instrumentation/refactoring commitment in this phase | Not started